## Communication Plan
|  |  |  | TG 1 | MA’s of the policy instruments addressed; Regional, local and national authorities, (other) key policy and decision makers in regional, national and EU authorities
|  |  |  | TG 2 | Key stakeholder groups; Local and regional authorities, specifically professionals working in the economic and nature departments of these organisations, both in and outside partners' regions.
|  |  |  | TG 3 | Citizens and economic actors in the partner regions; Wider public.
|  |  |  | TG 4 | Key experts in national and EU authorities and institutions dealing with the project topic; Other national and European projects, to promote cross-fertilization with other projects dealing with the same topics and challenges; General and specialized networks, to provide the widest opportunity to favour exchange of experience.
|  |  |  | TG 5 | Project partners
Wildlife Economy |  |  |  |  | action to realise
Communication Plan |  |  |  |  | action realised |  |  |  |  | Phase 1 | [23 empty] | Phase 2
Activity | Coordi-nation | Partners Involved | number to realise | Target group(s) | [5 empty] | Semester 1 | [5 empty] | Semester 2 | [5 empty] | Semester 3 | [5 empty] | Semester 4 | [5 empty] | Semester 5 | [5 empty] | Semester 6
[16 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6
|  |  |  | TG 1 | TG 2 | TG 3 | TG 4 | TG 5 |  | 1/8/19 – 31/1/20 | [5 empty] | 1/2/20 – 31/7/20 | [5 empty] | 1/8/20 – 31/1/21 | [5 empty] | 1/2/21 – 31/7/21 | [5 empty] | 1/8/21 – 31/1/22 | [5 empty] | 1/2/22 – 31/7/22
[9 empty] | Jul | Aug | Sep | Okt | Nov | Dec | Jan | Feb | Mrt | Apr | Mei | Jun | Jul | Aug | Sep | Okt | Nov | Dec | Jan | Feb | Mrt | Apr | Mei | Jun | Jul | Aug | Sep | Okt | Nov | Dec | Jan | Feb | Mrt | Apr | Mei | Jun | Jul
Events and Meetings
Partner meeting | PL + hosting partner | All | 6 | [12 empty] | ? | ? | [11 empty] | ? | ? | ? | bar: Apr to 1/2/21 – 31/7/21 Feb
Regional stakeholder meetings incl. workshops | PL | All | 28
Local dissemination events organized in the partner regions to inform the local population and visit the nature areas | PL | All | 7 | bar: 1/8/20 – 31/1/21 Aug to 1/2/21 – 31/7/21 Feb
Interregional peer2peer meetings (professionals in nature/economic departments and nature organisations) | PL, ALAVA, CAB | POM, DUH, RKLM, RS, RE | 9 | [12 empty] | ? | ? | bar: Apr to 1/8/20 – 31/1/21 Jan
Tailor made study visits (selection of key stakeholders per region) | RE | All | 4 | bar: Mei to 1/8/20 – 31/1/21 Jan
WLE conference | RLKM + PL | All | 1 | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Media
Project pages in the Interreg website | RLKM |  | 1 | bar: 1/8/20 – 31/1/21 Aug to 1/2/21 – 31/7/21 Feb
Update of project pages in the Interreg website every semester | RLKM | All | 6 | bar: 1/8/20 – 31/1/21 Aug to 1/2/21 – 31/7/21 Feb
Information about WLE project on institutional websites of all partners + updates | RLKM | All | 8 | bar: 1/8/20 – 31/1/21 Aug to 1/2/21 – 31/7/21 Feb
E-newsletters | RLKM | All | (4) 5 | bar: Apr; 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
The Rewilding Europe newsletter 3000 subscribers | RE | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Press releases | RLKM | All | 5 | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Social Media | RLKM | All | 24
Media coverage | RLKM | All
Publications
Prizes and competitions (e.g. best picture / selfie) to draw attention of the public (at least 2 actions during the project lifespan) | RWE | ? | 2 | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Project brochure | RLKM | LP, RE | 1 | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Project poster A3, to be displayed at partners premises and on the occasion of all the meetings and events | RLKM | All | 1 | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Articles and documentaries by Rewilding Europe (every few months major publications in international magazines like National Geographic, BBC Magazine, Travel Magazines and national media in the countries where RE is active (outreach > 50 mln. people/year) - not necessarily directly related to the WLE project | RE | All | [13 empty] | ? | ? | [11 empty] | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | bar: Apr to 1/2/21 – 31/7/21 Feb
Scientific articles in specialised media: there is a lot of scientific interest in the approach of Rewilding Europe, which can be used to generate scientific publications on WLE - not necessarily directly related to the WLE project | RE | All | [26 empty] | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | bar: 1/8/20 – 31/1/21 Aug to 1/2/21 – 31/7/21 Feb
Study report sustainable business models | RLKM / ALAVA | All | 2
Public Relations
Regular contact with MA’s and crucial stakeholders | PL | All
Attend Interreg Europe Policy Learning Platform and Interreg Europe annual events to find synergy in activities to foster a dialogue allowing partners to interact with all the actors and stakeholders involved in this topic all over Europe, giving the possibility to participate also to regions not directly involved in the project | PL | RE | 1 | [12 empty] | ? | ? | [11 empty] | ? | ? | ? | ? | ? | bar: Apr to 1/2/21 – 31/7/21 Feb
Presentation at EC-day | PL | RE | 1 | [25 empty] | ? | ? | ? | ? | ? | bar: 1/8/20 – 31/1/21 Aug to 1/2/21 – 31/7/21 Feb
Contribute to online dialogue platform Rewilding Europe | ? | ? | [13 empty] | ? | ? | bar: Apr to 1/8/20 – 31/1/21 Jan
Exchange with IR-E IMPACT project | PL | PL | 1 | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Internal communication
Share relevant documents and project updates via a project intranet function | PL | All
Communication guideline | RLKM | All | 1 | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan
Feedback on experiences in study visits | PL | All | bar: 1/8/20 – 31/1/21 Aug to 1/8/20 – 31/1/21 Jan

## Communication Monitoring
Wildlife Economy
Communication monitoring | Communication realisations
| semester 1 | semester 2 | semester 3 | semester 4 | semester 5 | semester 6 | Sum | Goals cf. application
Partner meeting | [6 empty] | 0 | 6
Regional stakeholder meetings incl. workshops | [6 empty] | 0 | 28
Local dissemination events organized in the partner regions to inform the local population and visit the nature areas | [6 empty] | 0 | 7 | 1 NL/B, 1 DE, 1 ES, 4 SE
Interregional peer2peer meetings (professionals in nature/economic departments and nature organisations) | [6 empty] | 0 | 9
Tailor made study visits (selection of key stakeholders per region) | [6 empty] | 0 | 4
WLE conference | [6 empty] | 0 | 1
Media
Project pages in the Interreg website | 1 | [5 empty] | 1 | 1
Update of project pages in the Interreg website every semester | [6 empty] | 0 | 6
Average number of sessions at the project pages per semester (goals = 1200 per semester) | [6 empty] | 0
Information about WLE project on institutional websites of all partners + updates | [6 empty] | 0 | 8
E-newsletters | [6 empty] | 0 | 4(5)
The Rewilding Europe newsletter 3000 subscribers | [6 empty] | 0
Press releases | 1 | [5 empty] | 1 | 5
Social Media | [6 empty] | 0 | 24
Media coverage | [6 empty] | 0
Publications
Prizes and competitions (e.g. best picture / selfie) to draw attention of the public (at least 2 actions during the project lifespan) | [6 empty] | 0 | 2
Project brochure | [6 empty] | 0 | 1
Project poster A3, to be displayed at partners premises and on the occasion of all the meetings and events | 1 | [5 empty] | 1 | 1
Articles and documentaries by Rewilding Europe (every few months major publications in international magazines like National Geographic, BBC Magazine, Travel Magazines and national media in the countries where RE is active (outreach > 50 mln. people/year) | [6 empty] | 0
Scientific articles in specialised media: there is a lot of scientific interest in the approach of Rewilding Europe, which can be used to generate scientific publications on WLE | [6 empty] | 0
Study report sustainable business models | [6 empty] | 0 | 2
Public Relations
Regular contact with MA’s and crucial stakeholders | [6 empty] | 0
Attend Interreg Europe Policy Learning Platform and Interreg Europe annual events to find synergy in activities to foster a dialogue allowing partners to interact with all the actors and stakeholders involved in this topic all over Europe, giving the possibility to participate also to regions not directly involved in the project | [6 empty] | 0 | 1
Presentation at EC-day | [6 empty] | 0 | 1
contruibution to online dialogue platform Rewilding Europe | [6 empty] | 0
Exchange with IR-E IMPACT project | 1 | [5 empty] | 1 | 1
Internal communication
Share relevant documents and project updates via a project intranet function | [6 empty] | 0
Communication guideline | 1 | [5 empty] | 1 | 1
feedback on experience in study visits | [6 empty] | 0

## List of publications
Wildlife Economy
List of Publications
| Medium | Title | Date | Link
1 | radio interview | Interview David Bell, Norbotten County on Radio P4 Norbotten | 2019-08-24 | https://sverigesradio.se/sida/artikel.aspx?programid=98&artikel=7284204&fbclid=IwAR3UJ7OsqYjl3uKVGpi1vDKdT6fNgqV2-78xEjlU8osctlgbZGXimW1XrJ8
2 | press release | Press release 20190903 - WLE - Banen uit de natuur halen - Provincie Limburg | 2019-09-03
3 | article on website Grensland Actueel | Artikel in Fiske journalen - Sweden | 2019-09-02
4 | e-news letter | Newsletter Rewilding Europe - Policy push for Europe’s wildlife economy | 2019-09-10
5 | radio interview | Radio2_Interview EChristis about WLE | 2019-09-18
6 | TV coverage | TV coverage Norbotten following the press release (fast forward to 01:44): | 2019-09-20 | https://www.svtplay.se/video/23738914/lokala-nyheter-norrbotten/svt-nyheter-norrbotten-20-sep-08-05-2
7 | article on website Grensland Actueel | Geld voor GrensPark Kempen~Broek | 2019-09-19
8 | article in newsletter Groene Ruimte | Provincie Limburg wil banen uit natuur halen | 2019-09-04
9
10
11
12
13
14
15
Note on E9: Rutger van Raalten: ben benieuwd, maar link lijkt niet te werken? Goed als er in ieder geval een screenshot is als 'bewijs'