## CASTILLA Y LEÓN
ACTION | [6 empty] | Milestones
|  | 2019 |  |  |  | 2020 |  |  |  |  | 2021
| JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN | JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN
1 . REGIONAL ACTION PLAN FOR ALTERNATIVE ENERGY VEHICLES IN CASTILLA Y LEÓN |  |  | 1000 e-vehicles; 33 chargers on public roads; 66 public restricted chargers; 5 fast charging points; 33% budget used | [5 empty] | 1250 e-vehicles; 66 chargers on public roads; 132 public restricted chargers; 10 fast charging points; 66% budget used |  |  | 1500 e-vehicles; 100 chargers on public roads; 200 public restricted chargers; 15 fast charging points; 100% budget used
2. PURCHASING INCENTIVE PROGRAMME |  |  | 40 Applications, registered by CyL offices | [5 empty] | Further 40 Applications, registered by EREN then audited by CyL |  |  | 80% of allocated budget utilised
3. INCOME TAX DEDUCTION |  |  | Eligible applicants buying electric, or hybrid with full electric up to 40km | [5 empty] | Acquired cars declared through AEAT; 250 Applications |  |  | 500 Applications
4. TRAINING | [8 empty] | Students: 130 in AV, 180 in BU, 180 in LE, 60 in P, 135 in SA, 30 in SG, 30 in SO, 200 in VA, 55 in ZA. |  |  | Students: 130 in AV, 180 in BU, 180 in LE, 60 in P, 135 in SA, 30 in SG, 30 in SO, 200 in VA, 55 in ZA.
Ó

## KÄRNTEN
ACTION | [6 empty] | Milestones
|  | 2019 |  |  |  | 2020 |  |  |  |  | 2021
| JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN | JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN
1. Supporting the uptake and the further development of electrical vehicles | Kikoff of the action |  | 0.70% M1; 0.40% N1-N3; 0.26% M2-M3 | [5 empty] | 0.85% M1; 0.42% N1-N3; 0.28% M2-M3 |  |  | 0.90% M1; 0.45% N1-N3; 0.30% M2-M3
2. Developing the Competence Centre for Innovative Mobility (KIM) |  |  | Contact and 1 partnership signed | [5 empty] | Consortium for a project proposal |  |  | One office developed in See:Port; 1 proposal submitted

## LAZIO
ACTION | [6 empty] | Milestones
|  | 2019 |  |  |  | 2020 |  |  |  |  | 2021
| JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN | JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN
UPDATE AND INTEGRATION OF THE GUIDELINES FOR THE REGIONAL PLAN FOR ELECTRIC MOBILITY (RPEM) |  |  | Drafting of the updates/integrations to the existing “Guidelines for the Electric-Mobility Regional Plan” | [5 empty] | Formal endorsement of the “Regional Guidelines for the Electric-Mobility” and related annexes by Lazio Region through a Regional Government Act (Delibera di Giunta Regionale) |  |  | In case of political instability, the deadline indicated (December 2020) could be extended to June 2021 to include a “buffer period”

## MALTA
ACTION | [6 empty] | Milestones
|  | 2019 |  |  |  | 2020 |  |  |  |  | 2021
| JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN | JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN
1. Financial Incentives |  |  | Evaluation of the grants | [5 empty] | Evaluation of the grants |  |  | Preliminary evaluation of the grants
2. The Deployment of Electric Buses on the Maltese Islands | Delivery of the new e-buses | Start of the operational phase in Gozo |  |  |  | Monitoring of the operational phase | [5 empty] | Assessment of the operational phase
3. Installation of eVehicles’ Roadside Charging Pillars |  |  | Montioring of the installation process | [5 empty] | Full installation of the charging pillars |  |  | Assessment of the operational phase

## PREŠOV
ACTION | Objectives | [6 empty] | Milestones
|  |  | 2019 |  |  |  | 2020 |  |  |  |  | 2021
|  | JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN | JUL-AUG | SEP-OCT | NOV-DEC | JAN-FEB | MAR-APR | MAY-JUN
1 . Popularizing and raising awareness of the phenomenon of electromobility and related trends in the Prešov region |  | Students awareness raising (through Phase 2) | Information Centre Project proposal | Establishing a functioning Information centre | Students awareness raising (through Phase 2) |  | Roadshows |  |  |  | Information day EUSEW | Roadshows
2. Reservation of parking spaces by zones |  |  | City parking zones setting | Design of intelligent parking system |  |  | Implementation of the system, trial operations | Routine operations from July on
3. Creating a regional subsidy microgrant scheme to promote e-mobility |  |  |  |  | Preparatory phase - agreements | Expert assessments and project review |  | Launch of the grant scheme | Launch of the grant scheme | Evaluation of applications | Drawing of the grant |  | Towards final inspection and evaluation
4. e-vehicle sharing (concept) |  |  |  | Preparatory phase completed |  |  | Feasibility study for selected solutions |  |  |  | Kickoff of the implementation phase | Test operations | Evaluation and inspection activities
5. Public e-transport in specific protected landscape areas of Prešov region |  |  |  | Builds on Action 1 | [5 empty] | Builds on Action 1 |  |  | Builds on Action 1
Š